TERMS OF REFERENCE

Cooperative Business Management Capacity Building Training Program

Assignment Country: Rwanda

- About IFC

The International Finance Corporation (IFC), the private sector investment arm of the World Bank Group (WBG), pursues its mission of reducing poverty and improving people’s lives by promoting private sector development through investment and advisory services. Building on IFC’s mission, Agribusiness Advisory promotes sustainable business practices to encourage good corporate governance, build the capacity of farmers, support women, and support management and investment decisions that are sustainable and inclusive. The World Bank Group Country Partnership Strategy in Rwanda includes a number of objectives aimed at improved access to inputs, financing and markets for smallholder farmers and improved agricultural value chains.

The Government of Rwanda Third Strategic Plan for the Transformation of Agriculture in Rwanda (2013-2018), seeks to facilitate the development of Rwanda’s agriculture, through a market based approach and a focus on export diversification and private sector driven value chains. The strategic vision is centered on a greater involvement of the private sector to increase agricultural exports, processing and value addition.

- Project Background

IFC Agribusiness Advisory works to catalyze the development of markets that work for all members of society. Through its Agribusiness Advisory services, the IFC is implementing agribusiness projects in Rwanda with the objective to increase the quantity of horticulture products procured from smallholder famers who are organized into cooperatives. An emerging need is to improve the business management capability of the cooperatives so that they function more efficiently as businesses, provide better services to their members and become more effective and reliable suppliers of horticulture products to buyers.

IFC advisory services and Scope Insight have co-developed a benchmarking and assessment tool (SCOPE Basic) that is used to measure the level of business professionalism of producer organizations, including cooperatives.  The objective of the tool is to systematically measure management capability in relation to eight performance dimensions: internal management, operations, financial management, supply, market, external risks, enablers, and sustainability. The assessment generates a numerical score on a scale of 0 to 5 for each performance dimension as well as an overall composite score. The numerical scores provide a transparent guide to the level of professionalism of the participating producer organizations and their strength and credibility in the supply chain. The scores also identify specific capacity gaps that can be used to develop tailored training programs for the producer organizations participating in the project.

- Description of Assignment

IFC intends to contract a firm (“the consultant”) to design and implement a business management capacity building program for producer organizations. The program will initially cover approximately 20 producer organizations, mostly co-operatives, involved in export focused horticulture activities. The proposed program will be carried out over a period of two years. Additional producer organizations might be added in the future.

The ultimate objective of the project is to increase the professionalism of horticulture producer organizations in Rwanda and thereby increase their ability to effectively contract with and supply an increased quantity of export-quality horticulture products to commercial buyers. Professionalism will be measured by raising and maintaining the SCOPE Basic scores for all participating producer organizations to a level of at least 3.5 on the 0 to 5 scale.  The qualifying score of 3.5 or above will be measured by a third party assessor.

The initial baseline SCOPE Basic assessments of the selected producer organizations took place in May 2016 and the results form a “needs assessment” for the training program. The actual assessment scores will be shared with the “Consultant” in anonymized version.

The consultant will be expected to develop and deliver a training program incorporating feedback from different parties (trainers, trainees, NAEB and IFC) and analyzing the results of the SCOPE Basic assessments.

The second Scope Basic assessment, which will measure the improvements after the first phase of training, is anticipated in June 2017.

4.	The specific tasks include:

- Understand the project context, including (i) the main project documents; (ii) the May 2016 SCOPE Basic assessments (to be shared with selected consultants); (iii) IFC’s draft training curriculum (Attachment 2); (iv) IFC’s performance objectives which define capabilities expected of producer organizations at different levels of professionalism [Attachment 3].

- Design business management capacity training program for the upcoming calendar year using the training materials and performance objectives provided as well as additional material contributed by the consultants

- Adapt the existing training material to create a customized Rwanda specific training curriculum covering the different levels of capability as described in the performance objectives.  The training material will include resources for both trainers and trainees in English and Kinyarwanda.

- Generate a tailored learning and development plan for each participating producer organization highlighting the top three improvements expected in the year ahead

- Develop a simple guide on how the trainees will share their acquired knowledge with other members of their producer organization

- Implement the producer business management training program for all participating organizations.  In the first phase this will cover approximately 20 organizations.  Additional organizations may be added in a second phase [phase 2 is subject to agreement].

- Gather feedback from trainers and trainees on the effectiveness of the training program especially in relation to the “top three” expected improvements at each coop.

- Adjust the training according to the results of the annual SCOPE Basic assessment for all participating co-operatives including a feedback session with the leaders of the producer Gather feedback from IFC and partners, trainers and trainees on the effectiveness organizations to address the new identified needs

- Summarize the main lessons learnt in a short summary document at the end of each calendar year.

- Generate additional contributions to training curriculum including at least four new local case studies per year.

- Edit the training content and approaches on the basis of the lessons learnt.

- Share lessons learnt with IFC, other project implementation partners and with other coop capacity building programs in Rwanda and possibly regionally.

- DELIVERABLES/SPECIFIC OUTPUTS EXPECTED FROM CONSULTANT

The consultant will be carrying out the assignment to increase the professionalism of horticulture producer organizations in Rwanda and thereby increase their ability to effectively contract with and supply. The main indicators of the professionalism will be an increased quantity of export-quality horticulture products to commercial buyers and raised overall SCOPE Basic scores for all participating cooperatives to a qualifying score of 3.5 and above, will in addition work towards attaining the following deliverables as expected on an annual basis (by December 30 in each year) are:

| Deliverable No. | Type of Deliverable | Schedule |
| --- | --- | --- |
| 1. | A cooperative business management capacity training program for the upcoming calendar year. | 0,5 month after contracting |
| 2. | Updated training materials for both trainers and trainees in English and Kinyarwanda. | 2 months after contracting |
| 3. | A tailored learning and development plan for each participating cooperative highlighting the top three expected improvements expected over the coming year and reflections on any previous learning and development plans. | Annually- 1 month before the start of training program for 2 years |
| 4. | A guide on how the trainees with share knowledge with other cooperative members | 2 months after contracting |
| 5. | An adjusted training content basing on the SCOPE Basic assessment, report and feedback session for each of the participating co-operatives. | By 30th March of every year for 2 years |
| 6. | Additional contributions to the training curriculum including at least four new local case studies per year. | Before 10th December of every year for 2 years. |
| 7. | A training report for the assignment with detailed feedback and lessons learnt for each of the 20 producer organizations | Before 10th December of every year for 2 years. |

- Materials and information to be provided by IFC after the selection of the consultant

- main project documents,

- May 2016 SCOPE Basic assessments of participating producer organizations and background on the SCOPE methodology

- IFC’s draft training curriculum

- IFC’s performance objectives which define capabilities expected of coops at different levels of professionalism.

- Location and Duration

The assignment is based in Rwanda and will last for 2 years, but the number of working days will be 5 full months in total.  The assignment will require extensive and frequent travel to the headquarters of the producer organizations located in different districts of Rwanda: Gatsibo, Karongi, Muhanga, Ngoma , Nyagatare, Nyanza, Rubavu, Ruhango, Rulindo,Rusizi, etc.

- Qualification Criteria

- Expertise/Experience in Agriculture, Rural Development, and Agribusiness Supply Chains

- Expertise/Experience in Cooperative Business Management Training with at least 2 similar assignments performed in the last 3 years linking cooperatives to commercial supply chains and / or the financial sector;

- Proposed methodology and work plan basing on the terms of references

- Evidence of qualified Key Staff. Brief bio data of the key experts should be submitted.

Technical Evaluation Criteria (60%) and Financial 40%

| No. | Criteria | Weight score |
| --- | --- | --- |
| 1 | Experience/expertise of the consultants(s) specifically related to the assignment | 40 |
| 2 | Adequacy of the methodology and the proposed work plan in responding to the ToRs | 30 |
| 3. | Qualifications and competence of the key staff related to the assignment | 30 |